## Project Overview
Project Overview
1 | Project overview
| Project name |  | Hotel Management System
| Technology |  | Web PHP, Bootstrap, MySQL
| The main work of the system |  | Refer to details at Sheet "Requirement"
2 | Project Scope
| # | Stage | Handover products | Date of delivery | Person In Charge | Scope of work
| 1 | Functional design of the system | Documentation describes the functions of each display interface | 2020-11-08 | Development Team | Based on the function requirements (Reference Sheet "Requirement") to design the detailed functional treatment on each interface page.
[5 empty] | Customer | Review and test the product.
| 2 | Layout design | Site layout, icon (link CDN) | 2020-11-10 | Development Team | Perform a detailed design Layout of all interfaces of the system.
[5 empty] | Customer | Review and test the product.
| 3 | Building infrastructure system | Github, MySQL | 2020-11-15 | Development Team | Perform Construction and installation of the necessary infrastructure for the project
[5 empty] | Customer | Information verification, Account Admin of the infrastructure.
| 4 | Build system functions | Source code (Source code needs to work properly). Database (The database is MySQL using phpMyAdmin version 5.0.4). Document test | 2020-11-20 | Development Team | Code implementation of system functions Perform Test to ensure the system functionality is working properly and fully. Performing Demo for Party A about the built product.
[5 empty] | Customer | Product testing.
| 5 | System deployment | Documentation Deploy. | 2020-11-29 | Development Team | Deploy the product on A computer system
| 6 | System maintenance | The system works stably | 2020-12-29 | Development Team | Responding to all bugs arising of the system during the operation.
Note on D6: Author: Xuống dòng bằng tổ hợp phím Alt+Enter
Note on D7: Author: Click để xem

## Requirement
Requirement List
No. | User groups | Functional group | Function | Note
1 | System user | Account Management | Register an Account
Login/Logout
Forgot Password
Update Account Infomation
|  | Management of Customer Information | Search: Search with keywords
View: - Show by category - Show detailed information
|  | Management of rooms and services | Search: Search with keywords
Filter: - Filter by Address / Region - Filter by room type, price
View: - Show by category - Show detailed information
Reviews and Comments: - View/ Add/ Edit Comment
Contact: - Phone Number - Email - Network Social: Facebook, Zalo
|  | General function | Help
About
2 | System administrator | Functions used as a regular user |  | Refer to the functions of the "System user" group.
|  | Administrative functions | Add/ Modify/ Delete
|  | Reported statistics | Statistics information of locations by information: - Search - Contact Statistics: Day, Week, Month

## Commnunication Plan
Commnunication Plan
# | Communication | Phương thức | Thời gian thực hiện
1 | Weekly Report: Bên B gửi báo cáo tiến độ của các công việc đã thực hiện trong tuần cho Bên A | Email | Thứ 2 và Thứ 5 hằng tuần
2 | Demo Sản phẩm: Thực hiện Demo sản phẩm đã đạt được | Google Meet | Thực hiện theo plan của dự án
3 | Bàn giao sản phẩm: Bên B thực hiện bàn giao sản phẩm cho bên A qua Email | Git, Github | Cập nhật hằng tuần
4 | Nghiệm thu sản phẩm: Bên A thực hiện nghiệm thu sản phẩm qua Email | Git, Github | Thực hiện theo plan của dự án